## README
QuickFlow Mock Dataset
Arquivo criado para testar importacao do QuickFlow com dados semelhantes a um export do Jira.
Planilhas
README | Guia rapido de uso.
Jira_Mock_Data | Base principal para importacao, com itens concluidos e itens em WIP.
Expected_Reference | Metricas de referencia para comparar o resultado do site.
Colunas principais
Ready for Development | Marco de compromisso usado para lead time.
Done | Data final de entrega em producao.
Current Column | Coluna atual do fluxo para teste de aging WIP.
Aging WIP (days) | Envelhecimento atual do item em andamento.
Sugestao
Importe a aba Jira_Mock_Data como .xlsx no site e confira throughput, cycle time, aging e percentis.

## Jira_Mock_Data
Issue Key | Summary | Issue Type | Status | Priority | Squad | Assignee | Labels | Created | Updated | Resolved | Ready for Development | In Development | Ready for Test | In Test | Deploy to Production | Done | Current Column | Current Column Entered At | Lead Time (days) | Cycle Time (days) | Aging WIP (days) | Blocked Days | Story Points | Source | Board
KAN-101 | Estruturar backlog inicial do produto | Story | Done | High | Core | Joao | discovery, backlog | 2025-12-30 10:00 | 2026-01-05 10:00 | 2026-01-05 10:00 | 2026-01-01 10:00 | 2026-01-02 04:00 | 2026-01-03 04:00 | 2026-01-04 04:00 | 2026-01-05 04:00 | 2026-01-05 10:00 | Em Produção | 2026-01-05 10:00 | 4 | 3.25 | 0 | 0 | 2 | Jira Mock | KAN
KAN-102 | Criar pipeline inicial de CI | Task | Done | Medium | Platform | Ana | devops | 2026-01-01 10:00 | 2026-01-09 10:00 | 2026-01-09 10:00 | 2026-01-04 10:00 | 2026-01-04 18:00 | 2026-01-06 04:00 | 2026-01-07 04:00 | 2026-01-09 04:00 | 2026-01-09 10:00 | Em Produção | 2026-01-09 10:00 | 5 | 4.67 | 0 | 1 | 3 | Jira Mock | KAN
KAN-103 | Corrigir erro de autenticação no Jira | Bug | Done | High | Core | Carlos | jira, auth | 2026-01-04 10:00 | 2026-01-14 10:00 | 2026-01-14 10:00 | 2026-01-08 10:00 | 2026-01-08 18:00 | 2026-01-10 04:00 | 2026-01-11 04:00 | 2026-01-14 04:00 | 2026-01-14 10:00 | Em Produção | 2026-01-14 10:00 | 6 | 5.67 | 0 | 2 | 4 | Jira Mock | KAN
KAN-104 | Prototipar tela de overview | Spike | Done | Low | Growth | Marina | ux, prototype | 2026-01-10 10:00 | 2026-01-22 10:00 | 2026-01-22 10:00 | 2026-01-15 10:00 | 2026-01-16 04:00 | 2026-01-20 04:00 | 2026-01-21 04:00 | 2026-01-22 04:00 | 2026-01-22 10:00 | Em Produção | 2026-01-22 10:00 | 7 | 6.25 | 0 | 0 | 5 | Jira Mock | KAN
KAN-105 | Implementar rota health | Task | Done | Low | Platform | Joao | api | 2026-01-14 10:00 | 2026-01-28 10:00 | 2026-01-28 10:00 | 2026-01-20 10:00 | 2026-01-24 04:00 | 2026-01-25 04:00 | 2026-01-26 04:00 | 2026-01-28 04:00 | 2026-01-28 10:00 | Em Produção | 2026-01-28 10:00 | 8 | 4.25 | 0 | 1 | 6 | Jira Mock | KAN
KAN-106 | Criar contrato inicial da API | Story | Done | Medium | Core | Ana | api, contract | 2026-01-19 10:00 | 2026-01-30 10:00 | 2026-01-30 10:00 | 2026-01-21 10:00 | 2026-01-24 04:00 | 2026-01-26 04:00 | 2026-01-27 04:00 | 2026-01-30 04:00 | 2026-01-30 10:00 | Em Produção | 2026-01-30 10:00 | 9 | 6.25 | 0 | 2 | 7 | Jira Mock | KAN
KAN-107 | Criar endpoint de métricas iniciais | Story | Done | High | Core | Joao | metrics | 2026-01-27 10:00 | 2026-02-03 10:00 | 2026-02-03 10:00 | 2026-01-30 10:00 | 2026-01-30 18:00 | 2026-02-01 04:00 | 2026-02-02 04:00 | 2026-02-03 04:00 | 2026-02-03 10:00 | Em Produção | 2026-02-03 10:00 | 4 | 3.67 | 0 | 0 | 8 | Jira Mock | KAN
KAN-108 | Ajustar paginação de busca no Jira | Task | Done | Medium | Platform | Ana | jira, pagination | 2026-01-29 10:00 | 2026-02-07 10:00 | 2026-02-07 10:00 | 2026-02-02 10:00 | 2026-02-02 18:00 | 2026-02-04 04:00 | 2026-02-05 04:00 | 2026-02-07 04:00 | 2026-02-07 10:00 | Em Produção | 2026-02-07 10:00 | 5 | 4.67 | 0 | 1 | 9 | Jira Mock | KAN
KAN-109 | Corrigir parse de datas UTC | Bug | Done | High | Core | Carlos | timezone | 2026-02-01 10:00 | 2026-02-12 10:00 | 2026-02-12 10:00 | 2026-02-06 10:00 | 2026-02-07 04:00 | 2026-02-08 04:00 | 2026-02-09 04:00 | 2026-02-12 04:00 | 2026-02-12 10:00 | Em Produção | 2026-02-12 10:00 | 6 | 5.25 | 0 | 2 | 2 | Jira Mock | KAN
KAN-110 | Documentar configuração local | Task | Done | Low | Growth | Marina | docs | 2026-02-05 10:00 | 2026-02-18 10:00 | 2026-02-18 10:00 | 2026-02-11 10:00 | 2026-02-14 04:00 | 2026-02-16 04:00 | 2026-02-17 04:00 | 2026-02-18 04:00 | 2026-02-18 10:00 | Em Produção | 2026-02-18 10:00 | 7 | 4.25 | 0 | 0 | 3 | Jira Mock | KAN
KAN-111 | Refinar modelo de throughput | Spike | Done | Medium | Core | Joao | throughput, analytics | 2026-02-15 10:00 | 2026-02-25 10:00 | 2026-02-25 10:00 | 2026-02-17 10:00 | 2026-02-19 04:00 | 2026-02-22 04:00 | 2026-02-23 04:00 | 2026-02-25 04:00 | 2026-02-25 10:00 | Em Produção | 2026-02-25 10:00 | 8 | 6.25 | 0 | 1 | 4 | Jira Mock | KAN
KAN-112 | Adicionar métricas por squad | Story | Done | Medium | Growth | Marina | squad, metrics | 2026-02-15 10:00 | 2026-02-27 10:00 | 2026-02-27 10:00 | 2026-02-18 10:00 | 2026-02-19 04:00 | 2026-02-23 04:00 | 2026-02-24 04:00 | 2026-02-27 04:00 | 2026-02-27 10:00 | Em Produção | 2026-02-27 10:00 | 9 | 8.25 | 0 | 2 | 5 | Jira Mock | KAN
KAN-113 | Adicionar suporte a filtros por squad | Story | Done | Medium | Growth | Ana | filters | 2026-02-22 10:00 | 2026-03-02 10:00 | 2026-03-02 10:00 | 2026-02-26 10:00 | 2026-02-27 04:00 | 2026-02-28 04:00 | 2026-03-01 04:00 | 2026-03-02 04:00 | 2026-03-02 10:00 | Em Produção | 2026-03-02 10:00 | 4 | 3.25 | 0 | 0 | 6 | Jira Mock | KAN
KAN-114 | Configurar logs estruturados | Task | Done | Low | Platform | Carlos | observability | 2026-02-24 10:00 | 2026-03-06 10:00 | 2026-03-06 10:00 | 2026-03-01 10:00 | 2026-03-01 18:00 | 2026-03-03 04:00 | 2026-03-04 04:00 | 2026-03-06 04:00 | 2026-03-06 10:00 | Em Produção | 2026-03-06 10:00 | 5 | 4.67 | 0 | 1 | 7 | Jira Mock | KAN
KAN-115 | Corrigir bug no bucket semanal | Bug | Done | High | Core | Joao | weekly, throughput | 2026-02-27 10:00 | 2026-03-11 10:00 | 2026-03-11 10:00 | 2026-03-05 10:00 | 2026-03-05 18:00 | 2026-03-07 04:00 | 2026-03-08 04:00 | 2026-03-11 04:00 | 2026-03-11 10:00 | Em Produção | 2026-03-11 10:00 | 6 | 5.67 | 0 | 2 | 8 | Jira Mock | KAN
KAN-116 | Explorar indicadores de aging | Spike | Done | Medium | Growth | Marina | aging | 2026-03-08 10:00 | 2026-03-17 10:00 | 2026-03-17 10:00 | 2026-03-10 10:00 | 2026-03-11 04:00 | 2026-03-15 04:00 | 2026-03-16 04:00 | 2026-03-17 04:00 | 2026-03-17 10:00 | Em Produção | 2026-03-17 10:00 | 7 | 6.25 | 0 | 0 | 9 | Jira Mock | KAN
KAN-117 | Criar rota de sync manual | Task | Done | Medium | Platform | Ana | sync | 2026-03-13 10:00 | 2026-03-24 10:00 | 2026-03-24 10:00 | 2026-03-16 10:00 | 2026-03-20 04:00 | 2026-03-21 04:00 | 2026-03-22 04:00 | 2026-03-24 04:00 | 2026-03-24 10:00 | Em Produção | 2026-03-24 10:00 | 8 | 4.25 | 0 | 1 | 2 | Jira Mock | KAN
KAN-118 | Estabilizar endpoint overview | Story | Done | High | Core | Joao | overview | 2026-03-16 10:00 | 2026-03-29 10:00 | 2026-03-29 10:00 | 2026-03-20 10:00 | 2026-03-23 04:00 | 2026-03-25 04:00 | 2026-03-26 04:00 | 2026-03-29 04:00 | 2026-03-29 10:00 | Em Produção | 2026-03-29 10:00 | 9 | 6.25 | 0 | 2 | 3 | Jira Mock | KAN
KAN-119 | Ajustar ranking de prioridades | Task | Done | Low | Platform | Carlos | priority | 2026-03-22 10:00 | 2026-03-31 10:00 | 2026-03-31 10:00 | 2026-03-27 10:00 | 2026-03-27 18:00 | 2026-03-29 04:00 | 2026-03-30 04:00 | 2026-03-31 04:00 | 2026-03-31 10:00 | Em Produção | 2026-03-31 10:00 | 4 | 3.67 | 0 | 0 | 4 | Jira Mock | KAN
KAN-120 | Criar consulta de issues resolvidas | Task | Done | Medium | Core | Carlos | jira, search | 2026-03-23 10:00 | 2026-04-03 10:00 | 2026-04-03 10:00 | 2026-03-29 10:00 | 2026-03-29 18:00 | 2026-03-31 04:00 | 2026-04-01 04:00 | 2026-04-03 04:00 | 2026-04-03 10:00 | Em Produção | 2026-04-03 10:00 | 5 | 4.67 | 0 | 1 | 5 | Jira Mock | KAN
KAN-121 | Ajustar retorno para frontend | Story | Done | Medium | Growth | Marina | frontend, api | 2026-03-31 10:00 | 2026-04-08 10:00 | 2026-04-08 10:00 | 2026-04-02 10:00 | 2026-04-03 04:00 | 2026-04-04 04:00 | 2026-04-05 04:00 | 2026-04-08 04:00 | 2026-04-08 10:00 | Em Produção | 2026-04-08 10:00 | 6 | 5.25 | 0 | 2 | 6 | Jira Mock | KAN
KAN-122 | Corrigir erro em query parameter | Bug | Done | High | Core | Joao | querystring | 2026-04-02 10:00 | 2026-04-12 10:00 | 2026-04-12 10:00 | 2026-04-05 10:00 | 2026-04-08 04:00 | 2026-04-10 04:00 | 2026-04-11 04:00 | 2026-04-12 04:00 | 2026-04-12 10:00 | Em Produção | 2026-04-12 10:00 | 7 | 4.25 | 0 | 0 | 7 | Jira Mock | KAN
KAN-123 | Avaliar modelo hexagonal | Spike | Done | Low | Platform | Ana | architecture | 2026-04-08 10:00 | 2026-04-20 10:00 | 2026-04-20 10:00 | 2026-04-12 10:00 | 2026-04-14 04:00 | 2026-04-17 04:00 | 2026-04-18 04:00 | 2026-04-20 04:00 | 2026-04-20 10:00 | Em Produção | 2026-04-20 10:00 | 8 | 6.25 | 0 | 1 | 8 | Jira Mock | KAN
KAN-124 | Criar mock de throughput | Story | Done | High | Core | Joao | mock, throughput | 2026-04-14 10:00 | 2026-04-28 10:00 | 2026-04-28 10:00 | 2026-04-19 10:00 | 2026-04-20 04:00 | 2026-04-24 04:00 | 2026-04-25 04:00 | 2026-04-28 04:00 | 2026-04-28 10:00 | Em Produção | 2026-04-28 10:00 | 9 | 8.25 | 0 | 2 | 9 | Jira Mock | KAN
KAN-125 | Montar série semanal de abril | Task | Done | Low | Growth | Marina | weekly | 2026-04-20 10:00 | 2026-04-30 10:00 | 2026-04-30 10:00 | 2026-04-26 10:00 | 2026-04-27 04:00 | 2026-04-28 04:00 | 2026-04-29 04:00 | 2026-04-30 04:00 | 2026-04-30 10:00 | Em Produção | 2026-04-30 10:00 | 4 | 3.25 | 0 | 0 | 2 | Jira Mock | KAN
KAN-126 | Ajustar série mensal do gráfico | Task | Done | Low | Growth | Marina | chart | 2026-04-26 10:00 | 2026-05-03 10:00 | 2026-05-03 10:00 | 2026-04-28 10:00 | 2026-04-28 18:00 | 2026-04-30 04:00 | 2026-05-01 04:00 | 2026-05-03 04:00 | 2026-05-03 10:00 | Em Produção | 2026-05-03 10:00 | 5 | 4.67 | 0 | 1 | 3 | Jira Mock | KAN
KAN-127 | Criar teste do endpoint throughput | Task | Done | Medium | Platform | Ana | test | 2026-04-26 10:00 | 2026-05-05 10:00 | 2026-05-05 10:00 | 2026-04-29 10:00 | 2026-04-29 18:00 | 2026-05-01 04:00 | 2026-05-02 04:00 | 2026-05-05 04:00 | 2026-05-05 10:00 | Em Produção | 2026-05-05 10:00 | 6 | 5.67 | 0 | 2 | 4 | Jira Mock | KAN
KAN-128 | Corrigir duplicidade de itens resolvidos | Bug | Done | High | Core | Carlos | dedupe | 2026-04-27 10:00 | 2026-05-08 10:00 | 2026-05-08 10:00 | 2026-05-01 10:00 | 2026-05-02 04:00 | 2026-05-06 04:00 | 2026-05-07 04:00 | 2026-05-08 04:00 | 2026-05-08 10:00 | Em Produção | 2026-05-08 10:00 | 7 | 6.25 | 0 | 0 | 5 | Jira Mock | KAN
KAN-129 | Implementar agregação mensal | Story | Done | High | Core | Joao | aggregation | 2026-04-28 10:00 | 2026-05-11 10:00 | 2026-05-11 10:00 | 2026-05-03 10:00 | 2026-05-07 04:00 | 2026-05-08 04:00 | 2026-05-09 04:00 | 2026-05-11 04:00 | 2026-05-11 10:00 | Em Produção | 2026-05-11 10:00 | 8 | 4.25 | 0 | 1 | 6 | Jira Mock | KAN
KAN-130 | Organizar labels de produto | Task | Done | Low | Growth | Marina | labels | 2026-04-29 10:00 | 2026-05-14 10:00 | 2026-05-14 10:00 | 2026-05-05 10:00 | 2026-05-08 04:00 | 2026-05-10 04:00 | 2026-05-11 04:00 | 2026-05-14 04:00 | 2026-05-14 10:00 | Em Produção | 2026-05-14 10:00 | 9 | 6.25 | 0 | 2 | 7 | Jira Mock | KAN
KAN-131 | Corrigir data de corte do período | Bug | Done | High | Platform | Ana | date-range | 2026-05-11 10:00 | 2026-05-17 10:00 | 2026-05-17 10:00 | 2026-05-13 10:00 | 2026-05-13 18:00 | 2026-05-15 04:00 | 2026-05-16 04:00 | 2026-05-17 04:00 | 2026-05-17 10:00 | Em Produção | 2026-05-17 10:00 | 4 | 3.67 | 0 | 0 | 8 | Jira Mock | KAN
KAN-132 | Adicionar endpoint para drill-down | Story | Done | Medium | Core | Joao | drilldown | 2026-05-12 10:00 | 2026-05-20 10:00 | 2026-05-20 10:00 | 2026-05-15 10:00 | 2026-05-15 18:00 | 2026-05-17 04:00 | 2026-05-18 04:00 | 2026-05-20 04:00 | 2026-05-20 10:00 | Em Produção | 2026-05-20 10:00 | 5 | 4.67 | 0 | 1 | 9 | Jira Mock | KAN
KAN-133 | Revisar payload de resposta | Task | Done | Low | Core | Carlos | payload | 2026-05-12 10:00 | 2026-05-22 10:00 | 2026-05-22 10:00 | 2026-05-16 10:00 | 2026-05-17 04:00 | 2026-05-18 04:00 | 2026-05-19 04:00 | 2026-05-22 04:00 | 2026-05-22 10:00 | Em Produção | 2026-05-22 10:00 | 6 | 5.25 | 0 | 2 | 2 | Jira Mock | KAN
KAN-134 | Investigar benchmark de throughput | Spike | Done | Medium | Growth | Marina | benchmark | 2026-05-14 10:00 | 2026-05-26 10:00 | 2026-05-26 10:00 | 2026-05-19 10:00 | 2026-05-22 04:00 | 2026-05-24 04:00 | 2026-05-25 04:00 | 2026-05-26 04:00 | 2026-05-26 10:00 | Em Produção | 2026-05-26 10:00 | 7 | 4.25 | 0 | 0 | 3 | Jira Mock | KAN
KAN-135 | Padronizar nomenclatura de métricas | Task | Done | Low | Core | Joao | metrics | 2026-05-15 10:00 | 2026-05-29 10:00 | 2026-05-29 10:00 | 2026-05-21 10:00 | 2026-05-23 04:00 | 2026-05-26 04:00 | 2026-05-27 04:00 | 2026-05-29 04:00 | 2026-05-29 10:00 | Em Produção | 2026-05-29 10:00 | 8 | 6.25 | 0 | 1 | 4 | Jira Mock | KAN
KAN-136 | Ajustar mock para relatório executivo | Story | Done | Medium | Growth | Ana | executive | 2026-05-20 10:00 | 2026-05-31 10:00 | 2026-05-31 10:00 | 2026-05-22 10:00 | 2026-05-23 04:00 | 2026-05-27 04:00 | 2026-05-28 04:00 | 2026-05-31 04:00 | 2026-05-31 10:00 | Em Produção | 2026-05-31 10:00 | 9 | 8.25 | 0 | 2 | 5 | Jira Mock | KAN
KAN-137 | Criar comparação mensal | Story | Done | Medium | Growth | Ana | comparison | 2026-05-26 10:00 | 2026-06-02 10:00 | 2026-06-02 10:00 | 2026-05-29 10:00 | 2026-05-30 04:00 | 2026-05-31 04:00 | 2026-06-01 04:00 | 2026-06-02 04:00 | 2026-06-02 10:00 | Em Produção | 2026-06-02 10:00 | 4 | 3.25 | 0 | 0 | 6 | Jira Mock | KAN
KAN-138 | Ajustar rota para month | Task | Done | Medium | Core | Joao | month | 2026-05-29 10:00 | 2026-06-07 10:00 | 2026-06-07 10:00 | 2026-06-02 10:00 | 2026-06-02 18:00 | 2026-06-04 04:00 | 2026-06-05 04:00 | 2026-06-07 04:00 | 2026-06-07 10:00 | Em Produção | 2026-06-07 10:00 | 5 | 4.67 | 0 | 1 | 7 | Jira Mock | KAN
KAN-139 | Corrigir serialização do response | Bug | Done | High | Platform | Carlos | serialization | 2026-05-31 10:00 | 2026-06-11 10:00 | 2026-06-11 10:00 | 2026-06-05 10:00 | 2026-06-05 18:00 | 2026-06-07 04:00 | 2026-06-08 04:00 | 2026-06-11 04:00 | 2026-06-11 10:00 | Em Produção | 2026-06-11 10:00 | 6 | 5.67 | 0 | 2 | 8 | Jira Mock | KAN
KAN-140 | Documentar métricas de entrega | Task | Done | Low | Growth | Marina | docs, delivery | 2026-06-03 10:00 | 2026-06-16 10:00 | 2026-06-16 10:00 | 2026-06-09 10:00 | 2026-06-10 04:00 | 2026-06-14 04:00 | 2026-06-15 04:00 | 2026-06-16 04:00 | 2026-06-16 10:00 | Em Produção | 2026-06-16 10:00 | 7 | 6.25 | 0 | 0 | 9 | Jira Mock | KAN
KAN-141 | Refinar consultas para dashboard | Story | Done | High | Core | Joao | dashboard | 2026-06-11 10:00 | 2026-06-21 10:00 | 2026-06-21 10:00 | 2026-06-13 10:00 | 2026-06-17 04:00 | 2026-06-18 04:00 | 2026-06-19 04:00 | 2026-06-21 04:00 | 2026-06-21 10:00 | Em Produção | 2026-06-21 10:00 | 8 | 4.25 | 0 | 1 | 2 | Jira Mock | KAN
KAN-142 | Checar consistência dos totais | Task | Done | Medium | Platform | Ana | consistency | 2026-06-15 10:00 | 2026-06-27 10:00 | 2026-06-27 10:00 | 2026-06-18 10:00 | 2026-06-21 04:00 | 2026-06-23 04:00 | 2026-06-24 04:00 | 2026-06-27 04:00 | 2026-06-27 10:00 | Em Produção | 2026-06-27 10:00 | 9 | 6.25 | 0 | 2 | 3 | Jira Mock | KAN
KAN-143 | Criar visão mensal por prioridade | Story | Done | Medium | Core | Carlos | priority, month | 2026-06-21 10:00 | 2026-06-29 10:00 | 2026-06-29 10:00 | 2026-06-25 10:00 | 2026-06-25 18:00 | 2026-06-27 04:00 | 2026-06-28 04:00 | 2026-06-29 04:00 | 2026-06-29 10:00 | Em Produção | 2026-06-29 10:00 | 4 | 3.67 | 0 | 0 | 4 | Jira Mock | KAN
KAN-144 | Criar endpoint mock enriquecido | Story | Done | High | Core | Joao | mock | 2026-06-23 10:00 | 2026-07-03 10:00 | 2026-07-03 10:00 | 2026-06-28 10:00 | 2026-06-28 18:00 | 2026-06-30 04:00 | 2026-07-01 04:00 | 2026-07-03 04:00 | 2026-07-03 10:00 | Em Produção | 2026-07-03 10:00 | 5 | 4.67 | 0 | 1 | 5 | Jira Mock | KAN
KAN-145 | Ajustar resposta para série temporal | Task | Done | Medium | Growth | Marina | timeseries | 2026-06-26 10:00 | 2026-07-08 10:00 | 2026-07-08 10:00 | 2026-07-02 10:00 | 2026-07-03 04:00 | 2026-07-04 04:00 | 2026-07-05 04:00 | 2026-07-08 04:00 | 2026-07-08 10:00 | Em Produção | 2026-07-08 10:00 | 6 | 5.25 | 0 | 2 | 6 | Jira Mock | KAN
KAN-146 | Corrigir filtro por projeto no mock | Bug | Done | High | Core | Carlos | mock, project | 2026-07-04 10:00 | 2026-07-13 10:00 | 2026-07-13 10:00 | 2026-07-06 10:00 | 2026-07-09 04:00 | 2026-07-11 04:00 | 2026-07-12 04:00 | 2026-07-13 04:00 | 2026-07-13 10:00 | Em Produção | 2026-07-13 10:00 | 7 | 4.25 | 0 | 0 | 7 | Jira Mock | KAN
KAN-147 | Criar visão semanal para operações | Story | Done | Medium | Growth | Ana | weekly, ops | 2026-07-08 10:00 | 2026-07-19 10:00 | 2026-07-19 10:00 | 2026-07-11 10:00 | 2026-07-13 04:00 | 2026-07-16 04:00 | 2026-07-17 04:00 | 2026-07-19 04:00 | 2026-07-19 10:00 | Em Produção | 2026-07-19 10:00 | 8 | 6.25 | 0 | 1 | 8 | Jira Mock | KAN
KAN-148 | Organizar massa de teste de julho | Task | Done | Low | Platform | Joao | test-data | 2026-07-12 10:00 | 2026-07-25 10:00 | 2026-07-25 10:00 | 2026-07-16 10:00 | 2026-07-17 04:00 | 2026-07-21 04:00 | 2026-07-22 04:00 | 2026-07-25 04:00 | 2026-07-25 10:00 | Em Produção | 2026-07-25 10:00 | 9 | 8.25 | 0 | 2 | 9 | Jira Mock | KAN
KAN-149 | Consolidar relatório mensal de julho | Story | Done | High | Growth | Marina | report | 2026-07-20 10:00 | 2026-07-29 10:00 | 2026-07-29 10:00 | 2026-07-25 10:00 | 2026-07-26 04:00 | 2026-07-27 04:00 | 2026-07-28 04:00 | 2026-07-29 04:00 | 2026-07-29 10:00 | Em Produção | 2026-07-29 10:00 | 4 | 3.25 | 0 | 0 | 2 | Jira Mock | KAN
KAN-150 | Preparar visão de agosto | Story | Done | Medium | Growth | Marina | forecast | 2026-07-22 10:00 | 2026-08-02 10:00 | 2026-08-02 10:00 | 2026-07-28 10:00 | 2026-07-28 18:00 | 2026-07-30 04:00 | 2026-07-31 04:00 | 2026-08-02 04:00 | 2026-08-02 10:00 | Em Produção | 2026-08-02 10:00 | 5 | 4.67 | 0 | 1 | 3 | Jira Mock | KAN
KAN-151 | Ajustar dados de tendência | Task | Done | Low | Core | Joao | trend | 2026-08-01 10:00 | 2026-08-09 10:00 | 2026-08-09 10:00 | 2026-08-03 10:00 | 2026-08-03 18:00 | 2026-08-05 04:00 | 2026-08-06 04:00 | 2026-08-09 04:00 | 2026-08-09 10:00 | Em Produção | 2026-08-09 10:00 | 6 | 5.67 | 0 | 2 | 4 | Jira Mock | KAN
KAN-152 | Corrigir desvio de timezone em agosto | Bug | Done | High | Platform | Carlos | timezone, august | 2026-08-06 10:00 | 2026-08-16 10:00 | 2026-08-16 10:00 | 2026-08-09 10:00 | 2026-08-10 04:00 | 2026-08-14 04:00 | 2026-08-15 04:00 | 2026-08-16 04:00 | 2026-08-16 10:00 | Em Produção | 2026-08-16 10:00 | 7 | 6.25 | 0 | 0 | 5 | Jira Mock | KAN
KAN-153 | Refatorar fonte mock compartilhada | Story | Done | Medium | Core | Ana | refactor | 2026-08-12 10:00 | 2026-08-24 10:00 | 2026-08-24 10:00 | 2026-08-16 10:00 | 2026-08-20 04:00 | 2026-08-21 04:00 | 2026-08-22 04:00 | 2026-08-24 04:00 | 2026-08-24 10:00 | Em Produção | 2026-08-24 10:00 | 8 | 4.25 | 0 | 1 | 6 | Jira Mock | KAN
KAN-154 | Fechar pacote de agosto | Task | Done | Medium | Platform | Joao | august, release | 2026-08-14 10:00 | 2026-08-28 10:00 | 2026-08-28 10:00 | 2026-08-19 10:00 | 2026-08-22 04:00 | 2026-08-24 04:00 | 2026-08-25 04:00 | 2026-08-28 04:00 | 2026-08-28 10:00 | Em Produção | 2026-08-28 10:00 | 9 | 6.25 | 0 | 2 | 7 | Jira Mock | KAN
KAN-201 | Consolidar relatorio executivo de julho | Story | Em Desenvolvimento | High | Core | Joao | aging, wip | 2026-06-30 10:00 | 2026-07-06 10:00 |  | 2026-07-04 10:00 | 2026-07-05 10:00 |  |  |  |  | Em Desenvolvimento | 2026-07-05 10:00 | 8 | 7 | 7 | 1 | 3 | Jira Mock | KAN
KAN-202 | Ajustar importacao de CSV do Jira | Task | Pronto para Desenvolvimento | Medium | Platform | Ana | aging, wip | 2026-07-03 10:00 | 2026-07-10 10:00 |  | 2026-07-08 10:00 | [5 empty] | Pronto para Desenvolvimento | 2026-07-08 10:00 | 4 | 3 | 4 | 2 | 4 | Jira Mock | KAN
KAN-203 | Investigar erro intermitente no parser | Bug | Em Testes | High | Core | Carlos | aging, wip | 2026-06-30 10:00 | 2026-07-08 10:00 |  | 2026-07-05 10:00 | 2026-07-06 10:00 | 2026-07-08 10:00 | 2026-07-09 10:00 |  |  | Em Testes | 2026-07-09 10:00 | 7 | 6 | 3 | 3 | 5 | Jira Mock | KAN
KAN-204 | Criar visao de aging por squad | Story | Pronto para Testes | Medium | Growth | Marina | aging, wip | 2026-06-30 10:00 | 2026-07-09 10:00 |  | 2026-07-07 10:00 | 2026-07-08 10:00 | 2026-07-11 10:00 |  |  |  | Pronto para Testes | 2026-07-11 10:00 | 5 | 4 | 1 | 4 | 6 | Jira Mock | KAN
KAN-205 | Preparar filtros por prioridade | Task | Em Desenvolvimento | Low | Growth | Marina | aging, wip | 2026-06-27 10:00 | 2026-07-03 10:00 |  | 2026-07-01 10:00 | 2026-07-02 10:00 |  |  |  |  | Em Desenvolvimento | 2026-07-02 10:00 | 11 | 10 | 10 | 1 | 7 | Jira Mock | KAN
KAN-206 | Automatizar carga de planilhas | Spike | Em Deploy para Produção | Medium | Platform | Ana | aging, wip | 2026-07-04 10:00 | 2026-07-11 10:00 |  | 2026-07-08 10:00 | 2026-07-09 10:00 | 2026-07-12 10:00 | 2026-07-13 10:00 | 2026-07-14 10:00 |  | Em Deploy para Produção | 2026-07-14 10:00 | 4 | 3 | -2 | 2 | 3 | Jira Mock | KAN
KAN-207 | Refinar legenda dos percentis | Task | Pronto para Desenvolvimento | Low | Core | Joao | aging, wip | 2026-06-29 10:00 | 2026-07-07 10:00 |  | 2026-07-05 10:00 | [5 empty] | Pronto para Desenvolvimento | 2026-07-05 10:00 | 7 | 6 | 7 | 3 | 4 | Jira Mock | KAN
KAN-208 | Validar dashboard com operacoes | Story | Em Testes | High | Growth | Carlos | aging, wip | 2026-06-26 10:00 | 2026-07-05 10:00 |  | 2026-07-03 10:00 | 2026-07-04 10:00 | 2026-07-07 10:00 | 2026-07-08 10:00 |  |  | Em Testes | 2026-07-08 10:00 | 9 | 8 | 4 | 4 | 5 | Jira Mock | KAN
KAN-209 | Padronizar colunas de exportacao | Task | Em Desenvolvimento | Medium | Platform | Ana | aging, wip | 2026-06-25 10:00 | 2026-07-01 10:00 |  | 2026-06-28 10:00 | 2026-06-29 10:00 |  |  |  |  | Em Desenvolvimento | 2026-06-29 10:00 | 14 | 13 | 13 | 1 | 6 | Jira Mock | KAN
KAN-210 | Montar amostra para treinamento interno | Story | Pronto para Testes | Low | Core | Marina | aging, wip | 2026-06-27 10:00 | 2026-07-04 10:00 |  | 2026-07-02 10:00 | 2026-07-03 10:00 | 2026-07-06 10:00 |  |  |  | Pronto para Testes | 2026-07-06 10:00 | 10 | 9 | 6 | 2 | 7 | Jira Mock | KAN

## Expected_Reference
Reference | Value
Overall P50 (days) | 6
Overall P85 (days) | 9
Overall P90 (days) | 9
Done issues | 54
Open issues | 10
Month | Throughput | Average Lead Time
2026-01 | 6 | 6.5
2026-02 | 6 | 6.5
2026-03 | 7 | 6.14
2026-04 | 6 | 6.5
2026-05 | 11 | 6.73
2026-06 | 7 | 6.14
2026-07 | 6 | 6.5
2026-08 | 5 | 7